## Progress Report
Contractor Monthly Progress Statement
Project: Hyderabad Urban Water Expansion – Phase II ¦ Month: August 2026
Blue = value taken from the source document; Black = calculated by formula.
Metric | Value | Unit | Remarks / Basis
Pipeline laying (contractor-reported)
Cumulative pipeline completion | 326 | km | Contractor statement
Claimed this month | 25 | km | Contractor statement
Implied cumulative at start of month | 301 | km | Calculated; matches 301 km in Monitoring Cell report
Contracted target | 500 | km | Assumption: from Report 1
% of contracted target | 65.2% | % | Calculated
Household connections & milestones
Household connections | 51800 | households | Contractor statement
Household target | 100000 | households | Assumption: from Report 1
% of household target | 51.8% | % | Calculated
Milestones completed | 14 | milestones | Contractor statement
Milestones total | 20 | milestones | Contractor statement
% milestones completed | 70% | % | Calculated
Progress & finance
Physical execution (contractor-reported) | 66% | % | Contractor statement
Financial utilisation (reported) | 72% | % | Contractor statement
Approved cost | 850 | ₹ crore | Contractor statement
Expenditure | 612 | ₹ crore | Contractor statement
Financial utilisation (calculated) | 72% | % | Cross-check of reported 72%
Cross-check against Monitoring Cell report (Report 1)
Monitoring Cell pipeline figure | 318 | km | Cross-reference to Report 1
Contractor claim above Monitoring Cell | 8 | km | Claim exceeds official figure
Monitoring Cell household figure | 54000 | households | Cross-reference to Report 1
Contractor figure vs Monitoring Cell | -2200 | households | Contractor reports fewer connections

## Evidence Association
Evidence Association
Associated indicator | Confidence | Evidence type | Source document | Reported value | Notes
Pipeline network completed | 78% | document | Contractor Monthly Progress Statement, Aug 2026 | 326 km | Contractor self-reported; claim is 8 km above the Monitoring Cell figure and 16 km above the field-verified figure.
Notes & assumptions
1. Confidence and evidence type supplied by user (78, document).
2. Assumption: 500 km contracted target taken from the Monitoring Cell report (Report 1).
3. Assumption: 100,000-household target taken from the Monitoring Cell report (Report 1).