## Progress Report
Household Beneficiary Survey
Project: Hyderabad Urban Water Expansion – Phase II ¦ Survey period: August–September 2026
Blue = value taken from the source document; Black = calculated by formula.
Metric | Value | Unit | Remarks / Basis
Sample
Households surveyed | 8500 | households | Survey
Households reporting active water connection | 5020 | households | Survey
Active connection rate in sample | 59.06% | % | Calculated
Households surveyed but not active | 3480 | households | Some connections installed but not yet operational
Project-wide estimates
Estimated households connected | 50400 | households | Survey estimate
Household target | 100000 | households | Assumption: from Report 1
Estimated % of target | 50.4% | % | Calculated
Sample as % of estimated connected households | 16.87% | % | Calculated
Estimated people with improved access | 236000 | people | Survey estimate
People per connected household | 4.6825 | people | Calculated
Cross-check against other sources
Monitoring Cell households | 54000 | households | Cross-reference to Report 1
Survey estimate vs Monitoring Cell | -3600 | households | Survey counts operational connections only
Field-verified households | 49600 | households | Cross-reference to Report 3
Survey estimate vs Field verification | 800 | households | Close agreement
Survey confidence | 81% | % | Survey

## Evidence Association
Evidence Association
Associated indicator | Confidence | Evidence type | Source document | Reported value | Notes
Households connected | 81% | survey | Household Beneficiary Survey, Aug–Sep 2026 | 50,400 households | Survey-based estimate. Physically installed but non-operational connections may be excluded.
Notes & assumptions
1. Confidence and evidence type supplied by user (81, survey).
2. Assumption: 100,000-household target taken from the Monitoring Cell report (Report 1).
3. Sample rate (59%) is not extrapolated; the 50,400 project-wide estimate is the survey's own figure.