## Progress Report
Field Inspection Report
Project: Hyderabad Urban Water Expansion – Phase II ¦ Inspection date: 10 September 2026 ¦ By: Independent Field Monitoring Team
Blue = value taken from the source document; Black = calculated by formula.
Metric | Value | Unit | Remarks / Basis
Inspection scope
Active construction zones covered | 3 | zones | Inspection note
Physically verified quantities
Pipeline network physically observed | 310 | km | Inspection note
Household connections physically verified | 49600 | households | Inspection note
Contracted target | 500 | km | Assumption: from Report 1
Verified pipeline as % of target | 62% | % | Calculated
Household target | 100000 | households | Assumption: from Report 1
Verified connections as % of target | 49.6% | % | Calculated
Variance vs other sources
Monitoring Cell pipeline figure | 318 | km | Cross-reference to Report 1
Field vs Monitoring Cell | -8 | km | Negative = field verified less than reported
Contractor pipeline claim | 326 | km | Cross-reference to Report 2
Field vs Contractor | -16 | km | Negative = field verified less than claimed
Field as % of Contractor claim | 95.09% | % | Calculated
Inspector findings
Commissioning status | Partial |  | Several recently reported sections not yet fully commissioned
Construction activity | Active |  | Work continuing in all inspected zones
Quality | Checks needed |  | Some sections require additional quality checks
Inspector confidence | 86% | % | Inspection note

## Evidence Association
Evidence Association
Associated indicator | Confidence | Evidence type | Source document | Reported value | Notes
Pipeline network completed | 86% | field_update | Field Inspection Note, 10 Sep 2026 (Independent Field Monitoring Team) | 310 km | Physically observed; lowest pipeline figure of the sources, likely because uncommissioned sections were excluded.
Notes & assumptions
1. Confidence and evidence type supplied by user (86, field_update).
2. Assumption: 500 km contracted target taken from the Monitoring Cell report (Report 1).
3. Assumption: 100,000-household target taken from the Monitoring Cell report (Report 1).