## Progress Report
Hyderabad Water Programme: June 2026 Progress Update
Includes trend comparison against August 2026 (Report 1)
Blue = value taken from the source document; Black = calculated by formula.
Metric | Value | Unit | Remarks / Basis
June 2026 position
Pipeline network completed | 275 | km | Source update
Household connections | 42000 | households | Source update
People covered | 190000 | people | Source update
Major milestones completed | 12 | of 20 | Source update
Overall physical progress | 57% | % | Source update
Expected progress | 68% | % | Source update
Progress gap (actual – expected) | -11% | % pts | Behind schedule if negative
People per connected household | 4.5238 | people | Calculated
Contracted target | 500 | km | Assumption: from Report 1
Pipeline as % of target | 55% | % | Calculated
Trend: June → August 2026 (August values from Report 1)
August pipeline completed | 318 | km | Cross-reference to Report 1
Pipeline added | 43 | km | 2 months
August household connections | 54000 | households | Cross-reference to Report 1
Connections added | 12000 | households | 2 months
August people covered | 243000 | people | Cross-reference to Report 1
People added | 53000 | people | 2 months
August milestones completed | 14 | of 20 | Cross-reference to Report 1
Milestones added | 2 | milestones | 2 months
August overall physical progress | 64% | % | Cross-reference to Report 1
Progress change | 7% | % pts | Calculated
Average pipeline added per month | 21.5 | km/month | Calculated

## Evidence Association
Evidence Association
Associated indicator | Confidence | Evidence type | Source document | Reported value | Notes
Pipeline network completed | 90% | report | Hyderabad Water Programme – June 2026 Progress Update | 275 km | Historical baseline for trend analysis.
Notes & assumptions
1. Confidence and evidence type supplied by user (90, report).
2. Assumption: 500 km contracted target taken from the Monitoring Cell report (Report 1).