## Progress Report
Hyderabad Urban Water Expansion – Phase II: Monthly Progress Report
Reporting period: August 2026 ¦ Prepared by: Hyderabad Urban Water Programme Monitoring Cell
Blue = value taken from the source document; Black = calculated by formula.
Metric | Value | Unit | Remarks / Basis
Pipeline network
Contracted target | 500 | km | Contract
Completed as of 31 Aug 2026 | 318 | km | Source report
Completed previous month | 301 | km | Source report
Added during August | 17 | km | Calculated
Remaining | 182 | km | Calculated
% of target completed | 63.6% | % | Calculated (reported overall physical progress is 64%)
Household connections
Target | 100000 | households | Source report
Connections completed | 54000 | households | Source report
% of target | 54% | % | Calculated
Remaining | 46000 | households | Calculated
Beneficiary coverage
Estimated people covered | 243000 | people | Source report
People per connected household | 4.5 | people | Calculated
Milestones
Target | 20 | milestones | Source report
Completed | 14 | milestones | Source report
% completed | 70% | % | Calculated
Financial
Approved project cost | 850 | ₹ crore | Source report
Expenditure to date | 612 | ₹ crore | Source report
Financial utilisation | 72% | % | Calculated
Balance available | 238 | ₹ crore | Calculated
Overall progress
Overall physical progress | 64% | % | Source report
Expected progress | 72% | % | Source report
Progress gap (actual – expected) | -8% | % pts | Behind schedule if negative

## Evidence Association
Evidence Association
Associated indicator | Confidence | Evidence type | Source document | Reported value | Notes
Pipeline network completed | 92% | report | Monthly Progress Report, Aug 2026 (Monitoring Cell) | 318 km | Evidence type not stated in source; 'report' assumed. Highest-level official figure.
Notes & assumptions
1. Confidence supplied by user (92).