## Project Overview
Field | Value
Project Name | Hyderabad Urban Water Expansion — Phase II
Project Type | Water
Sector | Urban Water & Sanitation
State | Telangana
Location | Hyderabad
Start Date | 2025-04-01
Target Date | 2027-03-31
Approved Cost (₹ Cr) | 850
Current Expenditure (₹ Cr) | 612
Expected Overall Progress (%) | 72
Status | At Risk
Purpose | Synthetic test portfolio for ProjectVision AI evidence extraction, recommendation, consistency and intelligence testing

## Objectives & Metrics
Objective | Objective Weight | Metric | Kind | Unit | Baseline | Target | Current Value | Expected Value | Metric Weight | Evidence Required
Network Expansion | 45 | Pipeline network completed | quantity | km | 0 | 500 | 310 | 360 | 70 | Yes
Network Expansion | 45 | Major pipeline milestones completed | milestone | milestones | 0 | 20 | 14 | 15 | 30 | Yes
Household Water Connections | 55 | Households connected | count | households | 0 | 100000 | 54000 | 70000 | 75 | Yes
Household Water Connections | 55 | People covered | beneficiaries | people | 0 | 450000 | 248000 | 315000 | 25 | Yes

## Evidence Register
Evidence ID | Source | Evidence Type | Reporting / Inspection Date | Metric | Value | Unit | Confidence % | Notes | Intended Test
EV-001 | Hyderabad Urban Water Programme Monitoring Cell | report | 2026-08-31 | Pipeline network completed | 318 | km | 92 | Official monthly progress report. Also contains households 54,000, people 243,000, milestones 14, physical progress 64%, expected 72%, expenditure ₹612 Cr. | Primary official source; test context and unit matching
EV-002 | Project Contractor | document | 2026-08-31 | Pipeline network completed | 326 | km | 78 | Contractor statement. Also contains households 51,800, milestones 14, physical execution 66%, financial utilisation 72%. | Messy multi-number document; test automatic candidate selection
EV-003 | Independent Field Monitoring Team | field_update | 2026-09-10 | Pipeline network completed | 285 | km | 86 | Field inspection value intentionally lower than other sources to create a stronger evidence discrepancy. | Stress-test evidence conflict
EV-004 | Household Beneficiary Survey | survey | 2026-09-01 | Households connected | 50400 | households | 81 | Survey estimates 50,400 connected households and 236,000 people receiving improved access. | Test metric/value recommendation
EV-005 | Hyderabad Water Programme | report | 2026-06-30 | Pipeline network completed | 275 | km | 90 | Older progress update: households 42,000, people 190,000, milestones 12/20, physical progress 57%, expected 68%. | Test stale evidence detection

## Evidence Documents
Evidence ID | Document Name | Document Content
EV-001 | Official_Monthly_Progress_Report_Aug_2026.txt | HYDERABAD URBAN WATER EXPANSION – PHASE II MONTHLY PROGRESS REPORT Reporting period: August 2026 Pipeline network: Contracted target: 500 km Completed as of 31 August 2026: 318 km Previous month: 301 km Household connections: Target: 100000 households Connections completed: 54000 households Beneficiary coverage: Estimated people covered: 243000 Major milestones: Completed: 14 Target: 20 Financial: Approved project cost: ₹850 crore Expenditure to date: ₹612 crore Overall physical progress: 64% Expected progress: 72% Report prepared by: Hyderabad Urban Water Programme Monitoring Cell
EV-002 | Contractor_Monthly_Progress_Statement_Aug_2026.txt | CONTRACTOR MONTHLY PROGRESS STATEMENT Project: Hyderabad Urban Water Expansion – Phase II Month: August 2026 Pipeline laying completed: 326 km Pipeline laying claimed this month: 25 km Cumulative pipeline completion: 326 km Household connections: 51,800 Major milestones: 14 completed out of 20 Physical execution reported by contractor: 66% Financial utilisation: 72% Approved cost: ₹850 crore Expenditure: ₹612 crore
EV-003 | Independent_Field_Inspection_10_Sep_2026.txt | FIELD INSPECTION NOTE Project: Hyderabad Urban Water Expansion – Phase II Inspection date: 10 September 2026 Site inspection covered three active construction zones. Verified pipeline network physically observed: 285 km Household connections physically verified: 49,600 Several recently reported pipeline sections were not yet fully commissioned. Construction activity remains active, but some sections require additional quality checks. Inspector confidence: 86% Inspection conducted by: Independent Field Monitoring Team
EV-004 | Household_Beneficiary_Survey_Aug_Sep_2026.txt | HOUSEHOLD BENEFICIARY SURVEY Project: Hyderabad Urban Water Expansion – Phase II Survey period: August–September 2026 Households surveyed: 8,500 Households reporting active water connection: 5,020 Estimated households connected across project area: 50,400 Estimated people receiving improved water access: 236,000 Survey confidence: 81% Some household connections were physically installed but not yet operational.
EV-005 | Older_Progress_Update_June_2026.txt | HYDERABAD WATER PROGRAMME JUNE 2026 PROGRESS UPDATE Pipeline network completed: 275 km Household connections: 42,000 People covered: 190,000 Major milestones: 12 / 20 Overall physical progress: 57% Expected progress: 68%

## Expected Checks
Test | Expected Behavior | Why It Matters
Metric context matching | EV-002 should recommend 'Pipeline network completed' rather than unrelated numeric fields. | Tests evidence → metric reasoning.
Unit matching | 326 should match the pipeline metric because the evidence says km. | Prevents selecting 14, 66 or 72 from the same document.
Multi-number extraction | The system should surface multiple candidates and rank them. | Real reports contain many numbers.
Evidence conflict | EV-001/002/003/005 contain materially different pipeline values; intelligence should flag discrepancy. | Tests evidence consistency.
Low confidence | If any source confidence is manually lowered below the engine threshold, a low-confidence signal should appear. | Tests measurement trust.
Stale evidence | EV-005 is intentionally older than the August/September sources. | Tests evidence recency.
Schedule gap | Current metric-derived progress should be below expected project progress. | Tests early-warning logic.
Cost gap | ₹612 Cr / ₹850 Cr ≈ 72% expenditure while physical delivery is lower. | Tests financial-vs-physical pressure.
Human confirmation | Recommendation should not silently overwrite the metric. | Protects data integrity.

## Baseline Calculations
Indicator | Calculation | Expected Result
Financial utilisation | 612 / 850 × 100 | 72
Pipeline current progress | (310 - 0) / (500 - 0) × 100 | 62
Pipeline expected progress | (360 - 0) / 500 × 100 | 72
Milestone progress | 14 / 20 × 100 | 70
Household connection progress | 54000 / 100000 × 100 | 54
People coverage progress | 248000 / 450000 × 100 | 55.1111
Pipeline evidence spread | (326 - 285) / 285 × 100 | 14.386